## CHIP 2022 Dashboard
|  |  | Key: | On track
Delayed
Paused or experiencing barriers
Complete
Strategy changed
Priority Area
1 Oral health | [6 empty] | Population | Activities | Process measurement | Outcome measurement | Notes
Outcome Measures |  |  | 2018 Baseline | 2020 Update | 2021 Update | Source
Increase the % of children in target schools who receive dental sealants by 6% |  |  | 26.5% children 6-14 | 27.3% children 6-14 2019 | sealants have ended as a metric; measure adjusted to utilization for children 6-14: 52.1% in this age group engaged | Capitol Dental claims
Demonstrate increase in consumption of fruits and vegetables through participant surveys |  |  | 0 reports received | 133 program participants reported consuming more produce | 323 Yamhill County and 340 Grand Ronde residents received food boxes from Grand Ronde Food Pantry (fruits, vegetables, meat, and dairy) | SNACK grantee report Master Gardeners' grantee report; 2021 Marion Polk Food Share grantee report
Increase engagement with dental care for members involved with peer support by 1% |  |  | 8.86% engagement with dental care overall, no peer support data | 7.56% engagement with dental care overall, no peer support data | Better data collection methods show 31.1% overall utilization of dental care in 2021 | YCCO member claims
reduce number of cavities in members by 1% |  |  | 1.1% members with risk caries | 1.48% members with risk caries | Better data collection methods show 19.5% with risk caries | Capitol Dental claims
Increase the rate of engagement for people in rural areas by 2% |  |  | No rural-specific data | No rural-specific data | Avg 29% people in rural zip codes have at least one dental visit in 2021, compared to avg 22% in larger towns or urban areas, avg 36% in McMinnville and Newberg; this data was relatively inconclusive and metric will be deleted for 2022 | Capitol Dental claims
Reduce the rate of cavities in students by 3% |  |  | 2.10% members <19 with risk caries | 2.01% members <19 with risk caries | Better data collection methods show 30.4% members with risk caries | Capitol Dental claims | Capitol Dental claims
Objective |  | Strategy | Narrative | Timeline |  | Partners | YCCO member claims
| 1 | [5 empty] | Capitol Dental claims
1.1 Increase understanding of oral health self-care and benefits for members | 1.1.1 | 1.1.1 Coordinate and deliver school-based oral health education, for at least one grade level in each school district. | After delays with education program delivery in schools because of Covid, Capitol Dental Care was able to deliver oral health supplies and educational materials to 6/7 school districts | 2021-06-01 | 2022-06-22 | 1-2 grade levels in each school district, Linfield, Chemeketa, and George Fox, Capitol Dental | children | oral health curriculum addition to health education classes, oral health education addition to GBG (Granny's Wacky Prizes), incorporate brushing or fluoride into school day, distribute dental supplies to schools (K-6 minimum) | supplies, consent forms, classrooms incorporating curriculum change, dental visits, dental sealants | Increase rate of dental sealants delivered to YCCO members by 6%; evaluation of oral health knowledge pre-post for GBG classrooms compared to non-GBG classrooms
| 1.1.2 | 1.1.2 Provide regular dental education, assessments, and sealants for members through existing community events, distributing educational materials at one community event in each school district area per year. | Capitol Dental Care delivered oral health supplies and educational materials to 6/7 school districts, in partnership with its outreach sealant and screening program | 2021-06-01 | 2022-06-22 | Capitol Dental | members | distribute oral health related materials at one event in every school district catchment area per year | number of materials distributed, number of community events attended, feedback forms from events | Increase rate of dental sealants delivered to YCCO members by 6%; evaluation of oral health knowledge pre-post for school districts recieving oral health education programs/materials
1.2 Increase availability of materials, foods, and supplies that promote oral health | 1.2.1 | 1.2.1 Improve access to free dental supplies by distributing through local services agencies, especially in rural areas; establish regular dental supply deliveries in at least one service agency per town by June 2021 | Capitol Dental Care delivered free oral health supplies to 6/7 school district catchment areas, a total of 2826 supplies distributed countywide | 2021-06-01 | 2022-06-22 | Capitol Dental | homeless members, members in unfluoridated areas | distribute free dental supplies through service agencies, schools, and partner business, targeting homeless population | Increase the % of children who receive dental sealants by 6%; reduce number of cavities in members by 2% | rate of caries among members; rate of engagement among members
| 1.2.2 | 1.2.2 Ensure access to healthy foods for key populations by funding programs like SNACK, VeggieRX, or community gardens; release RFP for funding by October 2019 | Nutrition Oregon Campaign workgroup formed, conducted robust needs assessment of nutrition needs and recommended strategies; convened cross-sector community workgroups to address different identified nutrition needs | 2021-03-01 | 2021-03-01 | food pantries, community gardens, schools, sherlters, university-based programs, churches, apartment complexes | Population - older adults and young children in rural Yamhill County area; OHP members | mobile food pantries, VeggieRx programs, SNACK, apartment or housing gardens, etc. | increase in knowledge, pre- post- survey, self-efficacy, quality of life, fruit and veggie consumpton, utilization or receipt of food, number impacted, school behavioral and attendence data, number organizations involved | Demonstrate increase in consumption of fruits and vegetables through participant surveys
1.3 Increase the number of locations members can receive dental services in the area | 1.3.1 | 1.3.1 Partner with local peer support agencies and other agencies to improve access to dental care, strengthening referral pathways and holding one training. | YCCO supported a CME event in 2021 called Trauma and the Dental Patient. The event targeted multidisciplinary providers, including behavioral health and THWs, and included information about connecting dental patients to behavioral health and vice versa. | 2020-06-01 | 2022-06-23 | Capitol Dental, peer support agencies | members experiencing mental health issues, substance use, or homelessness | promote oral health through peer support agencies by sharing materials, conduct trainings around oral health education in peer support agencies, colocate oral health services into peer centers | number of patients served in peer support agency settings, number of materials distributed, number of trainings conducted, training evaluation data | Increase engagement with dental care for members involved with peer support by 1%; reduce number of cavities in members by 1%
| 1.3.2 | 1.3.2 Partner with local Oral Health Coalition and Capitol Dental Care to explore teledentistry options in the community. | Oral Health Coalition continues to have representation from Medical Teams International mobile dentristry and mobile EPDHs are available at Capitol and regularly visit schools, events, and CBOs. Capitol Dental has 22 unique locations identified for teledentristry services, 16 of which have had YCCO member claims in 2021. | 2023-06-01 |  | Providence, VG, MDT, Public Health | members, especially rural, unengaged, and high ED users | incorporate teledentistry services into existing mobile and rural dental and medical clinics | occurences of services delivered using teledentistry technology | Increase the number of teledentistry tools and options available to the community | Meet and Greet – CME Spring CME – dental visit metric-related; pediatric dental visits Show MTI recruitment video Fall Meet and Greet – CME or fundraiser? Pledge program – donor levels Bring dental van for display/exhibit Keynote – Kelli Swanson-Jaecks To do: Emily reach out to CME committee – 8/28 Kyle reach out to ODA and ODHA about CE Whole group reaches out to dental contacts – tests ideas
1.4 Improve referral pathways and oral health integration efforts, including dental van volunteering | 1.4.1 | 1.4.1 Coordinate 1 oral health provider meet and greet event by December 2020 | YCCO continues to offer CME events to providers; strategy has graduated to more robust integration efforts between primary care and oral health, specifically for populations with diabetes and pregnant people | 2020-12-01 |  | Oral Health Coalition | providers | organize one meet-and-greet event for providers to share knowledge about integration of care, referral pathways, and develop relationships | number of events held, evaluation feedback | evaluation responses from providers before and after meet and greet (3 questions max)
1.5 Coordinate and Deliver an evidence-based oral health curriculum in YC schools to increase oral health self-care | 1.5.1 | 1.5.1 Conduct school assessment of current oral health curriculum. | Assessment completed 2019 | 2019-10-01 |  | YCPH | elementary students |  |  | Assessment of curriculum compiled
| 1.5.2 | 1.5.2 Distribute oral health supplies to schools within the community. | Capitol Dental, through a grant from YCCO CHIP funds, provided 2826 oral health supply and education kits to youth and community members in 2021. | 2021-12-01 | 2021-12-01 | YCCO | elementary students |  |  | Reduce the rate of cavities in students receiving supplies by 2%
| 1.5.3 | 1.5.3 Adopt an oral health Granny's Wacky Prize for the PAX program. | Changes to PAX delayed as training shifts to virtual and teachers undergo generalized refresher trainings as students return to the classroom. Three schools have signed up for refresher trainings in fall of 2022. | 2022-07-01 | 2022-07-01 | YCPH and schools | elementary students |  |  | Reduce the rate of cavities in students by 3%
| 1.5.4 | 1.5.4 Incorporate oral health components to one grade health curriculum. | Changes to curriculum delayed as students return to the classroom. Listening session held with Willamina high school students and tobacco/vaping prevention lesson added to Willamina School District middle and high school curriculum. | 2020-09-01 | 2022-09-20 | School districts, YCPH | elementary students |  |  | Reduce the rate of cavities in students by 1%
| 1.5.5 | 1.5.5 Adopt in-school fluoride or brushing routine in Kindergarten grade level in all rural school districts. | Changes to curriculum delayed as students return to the classroom. Capitol continues to do outreach and education in all school districts. | 2021-09-01 | 2021-09-20 | YCCO and Capitol and School Districts | elementary students |  |  | Reduce the rate of cavities in students in rural areas by 2%
Priority Area
2 Behavioral Health
Outcome Measures |  |  | 2018 Baseline | 2020 Update |  | Source
Increase rate of members attempting to quit using tobacco by 10% |  |  | 2017: 34 members of 25.5% prevalence; 32 accessing in-person classes | 52 of 22.8% prevalence; no in person classes | 19.9% prevalence; no in person classes | Yamhill County Optum Quit for Life, Willamette Valley Cancer Foundation | Yamhill County Optum Quit for Life, Willamette Valley Cancer Foundation
Demonstrate increase in knowledge for participants; increase rate of participants who advance in their field |  |  | no training offered | 4 peer support specialists with HHS advanced as Qualified Mental Health Associates. | 4 doulas trained and mentored; 30 peer support specialists received ongoing mindfulness training | HHS | HHS
Increase rate of people reporting suicidal ideation who do not complete suicide by 50% |  |  | 21.5/100,000 people completed suicide | 13.8/100,000 people completed suicide | no data yet available | 2018 Yamhill County Vital Records; 2019 HHS records | 2017, 2019 Oregon Healthy Teens YC
Reduce the number of patients receiving opioid prescriptions from multiple providers by 10% |  |  | 69.4% top prescribers in YC querying PDMP | 77.3% top presribers in YC querying PDMP | No data yet available | Prescribing and Drug Overdose Data Dashboard | PDMP data
Reduce the number of opioid deaths in the service area |  |  | 2019: 280 deaths | 2020: 472 total deaths | As causes of opioid deaths have shifted from prescriptions to fentanyl, strategy needs to shift to overall opioids: 2021: 473 deaths
Increase the rate of members accessing alternative pain management by 5% |  |  | 28 participants in Persistent Pain Program 2017 | 23 participants 2019 | PPP paused in 2021; no record of sessions | YCCO member claims | YCCO member claims
Reduce the rate of patients prescribed more than 50 MED by 1% Increase the rate of overdose patients who have engaged with care management services |  |  | 208 pts; 20.44/1000 people | 13.69/1,000 people | 2021 baseline: 27% | Prescribing and Drug Overdose Data Dashboard | Prescribing and Drug Overdose Data Dashboard
Reduce new rates of Hepatitis C by 1% |  |  | measure changed: 4% adults in HepC cohort screened; 423 needles given out | 9% adults screened; 926 needles collected, 426 given out | 85 individuals served; 6508 needles collected, 5607 given out | YCCO member claims; Provoking Hope Needle Exchange reporting | YCCO member claims, HepC outreach PIP; Provoking Hope and HHS Needle Exchange reporting
Objective |  | Strategy | Narrative | Timeline |  | Partners
2
2.1 Increase community access and awareness of tobacco cessation resources | 2.1.1 | 2.1.1 YCCO strategy: Promote Quitline through media outreach and materials in YCCO clinics by December 2019; materials available in all YCCO primary care clinics by June 2020; one informational session or training delivered for providers by December 2020 | Quitline promoted through YCCO member magazine mailed to all YCCO member households in March 2022. Quitline information shared with providers through site visit materials and behavioral health forum materials in Q4 2021 and Q1-2 2022. | 2023-12-01 | 2023-12-01 | YCPH, YCCO clinics | members who use tobacco | Promote Quitline through print materials, targeted outreach, and clinic education | # Quitline users, # tobacco users | Increase rate of members attempting to quit using tobacco by 5%
| 2.1.2 | 2.1.2 YCPH Strategy: Refer organizations to smoking cessation programs and facilitator trainings | PH staff repuporsed for COVID response; turnover has prevented fcused TPEP outreach. YCCO engaged with Confederated Tribes of Grand Ronde TPEP Coordinator to understand tribal-specific prevention materials. | 2021-06-01 | 2023-06-01 | YCPH- Cessation Materials ALA- Cessation programs and facilitator trainings American Cancer Society- Cessation Programs | YCCO clinics, peer support centers, shelters and food pantries, social service agencies | Deliver and share education materials around smoking cessation programs and facilitator trainings | # Quitline users, # tobacco users | Increase rate of members attempting to quit using tobacco by 1%
| 2.1.3 | 2.1.3 YCPH Strategy: Infuse tobacco cessation referral and counseling into Home Visiting programs and training | Home visiting trainings paused during the pandemic, but will restart in August 2022. 12 FamilyCore referrals for tobacco use prevention. | 2020-12-01 | 2022-12-22 | YCPH, Home visitor network, YCCO Family CORE Leadership | members who use tobacco | Deliver one training for home visiting network sharing information about motivation interviewing for tobacco cessation, Quitline referral pathways, and quit resources | # Quitline users, # participants | Increase rate of members who are parents attempting to quit using tobacco by 10%
2.2 Increase community-wide evidence-based suicide prevention trainings | 2.2.1 | 2.2.1 Offer upskilling and additional training for 15 existing peer support specialists, volunteers, and mental health employees by December 2022 | One PSS underwent training to support the Responsible Dads' Program; 6-PSS participated and completed MHACBO training. In the first part of 2022, YCCO partnered with a local peer support agency Provoking Hope to offer mindfulness training. Roughly 30-frontline mental health workers (THWs) and support staff participated in the 25-week self-care course led by a clinical social worker. Qualitative data from participants suggest learning and strengthening technics of self-efficacy, and relaxation. | 2021-12-01 | 2021-12-01 | YCCO, peer support agencies, HHS | volunteers and employees in mental-health related fields | Coordinate and promote training for mental health service providers to encourage local mental health providers are hired, professionally developed, and retained in the community | # participants in training, trainings held, scholarships offered, evaluation feedback | Demonstrate increase in knowledge for participants; increase rate of participants who advance in their field
| 2.2.2 | 2.2.2 Improve promotion of services via print materials, social media, and other awareness activities | YCPH Suicide Prevention Coordinator left role; new staff member to be hired. | 2021-06-01 | 2022-06-21 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members, general community | sharing information through the following methods: print materials through posting and mail, website and social media, in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, agencies involved | Increase rate of people reporting suicidal ideation who do not complete suicide by 50%
2.3 Increase awareness, education and utilization of pain management alternatives and appropriate prescription pain management | 2.3.1 | 2.3.1 Promote Prescription Drug Monitoring Program use among non-primary care providers | Chronic Non-Cancer Pain Workgroup continues to meet and promote best practices, but has shifted work towards addressing overdose deaths more than overprescribing, based on the shift in need. | 2020-11-01 | 2020-11-01 | YCPH | specialty and oral health care providers |  |  | Reduce the number of patients receiving opioid prescriptions from multiple providers by 10%
| 2.3.2 | 2.3.2 Review non-opioid pain management benefit options and services for YCCO members | Pain management options offered through Persistent Pain Program, starting up again, and through OHP-covered alternative services | 2023-11-01 | 2023-11-01 | YCCO | members experiencing chronic pain | assess covered alternative medicine benefits; promote available services and ensure providers have access to accurate information regarding alternative care benefits and referral and prior authorization activities | member feedback and complaints regarding alternative care; | rate of engagement with alternative pain management covered by YCCO; Compile alternative pain management resource guide; increase the rate of members accessing alternative pain management by 5%
| 2.3.3 | 2.3.3 Promote Oregon Pain Guidance practices to providers and community partners | Chronic Non-Cancer Pain Workgroup continues to meet and strategize for disseminating pain guidance | 2020-12-01 | 2020-12-01 | YCPH | providers and community partners | disseminate Pain Guidance information through provider network, serve as technical assistance resource for community regarding pain guidelines | # providers and agencies reached | Reduce the rate of patients prescribed more than 50 MED by 1%
| 2.3.4 | 2.3.4 Host one annual Opioid Summit to update the provider, community partners and community members about best practices and available resources | Opioid Summit canceled in 2021, being planned again for 2022 | 2019-11-01 | 2019-11-01 | YCPH | providers and community partners | Hold annual training for providers who work with patients experiencing pain, establish common understanding of current issues and best practices to address them | # participants, evaluation feedback | Reduce the rate of patients prescribed more than 50 MED; Demonstrate relevant information learned during Summit
| 2.3.5 | 2.3.5 Support community needle exchange program; launching program by December 2019; incorporating medical staff by 2022 | 109 instances of needle exchange support were provied in 2021-2, and of those 57 were referred to peer services, 100% were referred to some kind of services | 2020-12-01 | 2020-12-01 | YCPH, peer support | members who use drugs intravenously | Support needle exchange program, both mobile and fixed site delivery with additional peer or educational supports built in; incorporate medical staff by 2022 | # participants, rate of intravenous drug use-related disease, # materials distributed to participants, # needles provided and collected | Hepatitis C rates among members by 1%, % of wound-related ED visits
Priority Area
3 Children and Families
Outcome Measure |  |  | 2018 Baseline | 2020 Update |  | Source
Increase the rate of families connected to home visiting and other services |  |  | Avg Family CORE referrals: 60.5 per month; 726 overall | Avg Family CORE referrals: 40.5, 486 total in 2019; avg 38.1 in first 5 months of 2020 | Average FamilyCore referrals: 21, 254 total in 2021 | Family CORE referrals | YCCO claims data, incentive metric reports; Family CORE referrals
Decrease rate of postpartum depression by 2% |  |  | 11 diagnoses, ~3.6% of births | 33 diagnoses, ~11% of births | no update this quarter | YCCO member claims | YCCO member claims
Increase rate of dental screenings held in nonclinical settings by 10%; reduce rate of cavities in student by 2% |  |  | no data available for nonclinical settings | 2% of visits in nonclinical settings | 3.6% of visits were in nonclinical settings | Capitol Dental claims | Capitol Dental claims
Increase the rate of children receiving well-visits by 6% |  |  | 66.2% well-child | 62.2 well child 3-6 | 65.3% well child 3-6 | YCCO member claims, incentive metric reports
increase Kindergarten Assessment Scores |  |  | Approaches to Learning total: 3.6 avg rating/5 Early Math: 11.2 avg correct/16 Uppercase letter recognition: 14.4 avg correct/26 | Approaches to Learning total: 3.6 avg rating/5 Early Math: 11 avg correct/16 Uppercase letter recognition: 14.1 avg correct/26 | Kindergarten assessment redesigned for 2022 | Oregon Department of Education KA Scores
Objective |  | Strategy | Narrative | Timeline |  | Partners
3
3.1 Increase evidence-based care models that support community members, health care providers, and social service providers in achieving planned pregnancies | 3.1.1 | 3.1.1 Work with peer support agencies and other social service agencies to increase referrals to programs like Family CORE and encourage home visiting | The Yamhill County Community Doula group, comprise of state certified traditional health workers, are now a part of the home vising network supporting families and children. The doulas primarily engage (expecting) mothers and babies through the peripartum period to provide education, support, and engagement. Enhancing care coordination efforts by identifying and supporting families in the earlier stages of birth contributes to better social wellbeing. Council includes THW Liaison representative. | 2021-06-01 | 2021-06-01 |  |  |  |  | Increase the rate of children receiving well-visits by 6%; Increase the rate of post-partum well-visits by 6%
| 3.1.2 | 3.1.2 Conduct Family Wellbeing Assessment in all MMHs for all patients by June 2020. Connect at-risk mothers to behaviorist and home visiting supports. | Valley Women's Health was a top referrer to FamilyCore and into social programs, but closed in 2021. Strategy delayed as new OB partnerships are formed. | 2020-06-01 | 2023-06-01 | HHS/Public Health, YCCO | families with new babies | deliver and evaluate Family Well-Being Assessment for trauma scores and connect families with services if needed | number of assessments delivered, number of referrals made | Increase the number of screenings delivered by 25%
3.2 Create and implement a reproductive health education and marketing campaign. | 3.2.1 | 3.2.1 Distribute health promotion materials and information through a wide range of media, promoting availability of benefits, prenatal and postpartum care, CHW and doula supports, and family supports, and other health information and education by December 2021 | Continued Member Engagement Workgroup and outreach tracking for all events and materials. Developed two membership-wide mailings in 2021-2 with one in development, compared to one in 2020-21, alongside a social media and website Language Access campaign. From March 2022 to the end of May 2022, 1,110 FamilyCore rack cards were delivered and 5 FamilyCore Presentations were completed and 2 Unidos Resources Fairs: 1 on 4/27/2022 (30 rack cards), and 1 on 5/31/2022 (10 rack cards) . 2 Kindergarten Registration events: 4/29/2022 in Sheridan (30 rack cards) and 4/28/2022 Willamina (15 rack cards) | 2021-12-01 | 2021-12-01 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members of childbearing age | sharing information through the following methods: print materials through posting and mail, website and social media, in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, number of clinic calls and appointments made, effective contraceptive use; rate of engagement with prenatal care, rate of postpartum visits, % ECU, health births?, engagement with doula supports, rate of members accessing home visiting services | Increase the rate of children receiving well-visits by 6%; Increase the rate of post-partum well-visits by 6%; decrease rate of post-partum depression by 2%
3.3 Increase the availability of health-related services and screening at family-oriented events and activities | 3.3.1 | 3.3.1 Provide dental/vision/hearing screenings at annual Family Play Day outreach event and at Kinder Registration in three school districts by December 2021 | 2022- 2 Kindergarten Registration events Sheridan on 4/28/22 Willamina on 4/29/22 both events had vision, dental, hearing screenings along with parent survyes, information provided: PSP, FamilyCore, Parent Leadership Council, Mid Valley Parenting/Education We may not attend Family Play Day in 2022. | 2021-06-01 | 2021-06-01 | Early Learning Hub | families with children | offer medical screenings at Kinder Registration events in at least 3 school districts and at annual Family Play Day Event | number of materials distributed, number of community events attended, feedback forms from events | Increase rate of dental screenings held in non-clinical settings by 10%; reduce rate of cavities in student by 2%
| 3.3.2 | 3.3.2 Partner with 4 rural libraries to conduct outreach to families of children 0-5 and connect them to school readiness, family support, and healthcare services by June 2021 | Some KPI dollars were spent in October and December 2021: in Sheridan School District and McMinnville School District and Yamhill Enrichment Society: 5,267 chidren were engaged. 2021-22 Early Learning attended 36 events from June 2021 to August 2022, 31+ parent surveys were provided. Partner with McMinnville Parks and Rec and the McMinnville Library and the McMinnville Book Mobile. 3 Summer picnics (Sheridan 6/27/22, McMinnville 7/13/22 and Newberg 8/9/22). KPI dollars were spent in Sheridan School District and McMinnville School District and Yamhill Enrichment Society: 7,647 chidren were engaged, 2 Kindergarten Registration events: Sheridan on 4/28/22 Willamina on 4/29/22 both events had vision, dental, hearing screenings along with parent survyes, the ELH sent Kinder readiness outreach materials to families in the more rural school districts | 2021-06-01 | 2021-06-01 | Early Learning Hub | rural families with young children | attend rural library events and share materials with rural libraries around family support services | number of materials shared, number of events attended, number of referrals made from libraries | Increase the rate of children receiving well-visits by 6%; increase Kindergarten Assessment scores; increase rate of children from Spanish-speaking families receiving well-visits by 6%
| 3.3.3 | 3.3.3 Ensure access to healthy foods and physical activity for families by by funding programs like SNACK, VeggieRX, or community gardens. | Nutrition Oregon Campaign workgroup formed, conducted robust needs assessment of nutrition needs and recommended strategies; convened cross-sector community workgroups to address different identified nutrition needs | 2021-03-01 | 2021-03-01 | CAC | Families and children | Release an RFP and fund programs that are related to nutrition and physical activity |  | Demonstrate increase in consumption of fruits and vegetables through participant surveys ; increase the number of families connected to health-related services by 10%
Priority Area
4 Access to Care
Outcome Measure |  |  | 2018 Baseline | 2020 Update |  | Source
Increase engagement with primary care for people living in rural areas by 9% |  |  | 88.5% any claim 67.2% engaged with primary care | 83.6% any claim 66.8% engaged with primary care | 88.5% any claim 71.6% engaged only with primary care | YCCO claims data, incentive metric reports; Family CORE referrals | YCCO member claims
Increase rate of engagement for rural members by 12% |  |  | 88.5% | 83.6% | 88.5% | Capitol Dental claims | YCCO member claims
Demonstrate increase in knowledge around cultural agility through training evaluation surveys; 6-month follow-up surveys |  |  | 0 equity-based trainings offered | 1 trauma CME offered, one scheduled | 1 trauma CME offered, mindfulness training for THWs and emotional support for primary care provider CME offered | SNACK grantee report, OSU grantee report | CME post-event surveys
Reduce rate of clinical encounters where need for translation was not met |  |  | no data available | 75% members receiving language services don't have translation indicator in file | 71.5% members receiving services do not have an interpretation services flag | Claims, Mindlink and Passport to Languages invoices, clinic survey data | data process developing
Objective |  | Strategy | Narrative | Timeline |  | Partners
4
4.1 Increase community awareness of available services, rights, and benefits | 4.1.1 | 4.1.1 Distribute health promotion materials and information through a wide range of media, sharing healthy living information and education, benefit and resource information, member rights and advocacy, and invitations to engage | Continued Member Engagement Workgroup and outreach tracking for all events and materials. Developed two membership-wide mailings in 2021-2 with one in development, compared to one in 2020-21, alongside a social media and website Language Access campaign. Early Learning attended 36 events from June 2021 to August 2022, 31+ parent surveys were provided. | 2022-06-01 | 2022-06-01 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members, especially those unengaged with care or high ED utilizers | sharing information through the following methods: print materials through posting and mail, website and social media, targeted member phone calls (stratify by high risk tier members who are unengaged after 6 months of enrollment), in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, number of clinic calls and appointments made, ED utilization, contacts to customer service, screening rates, number of members actually contacted | Increase engagement with primary care for people living in rural areas by 9%; increase rate of people who are successfully engaged by phone or in-person within the first six months of enrollment to 70% | YCCO will provide community education on benefits to new and high risk OHP within the first 6 months of enrolling into the program though a multi media system; Build relationship with social services agency to provide wraparound services to OHP by provide educational materials on program eligibility for additional services. New member call from community workers on welcoming to OHP, streamline communication and building relationships with members. Navigator to help member utilize the system when they first join OHP.
| 4.1.2 | 4.1.2 Hold regular listening sessions and conduct regular surveys, in collaboration with clinics, to obtain feedback from patients, clients, and community members; Hold one listening session in each school district catchment area every two years; deliver surveys in at least one clinic annually | Held 13 stakeholder interviews, 10 listening sessions, and distributed surveys through 10 agencies and committees in the Yamhill County region. Listening sessions were held in 6 of the 7 SD catchment areas. Plans to deliver surveys around language access in clinics by 9/22. | 2022-06-01 | 2022-09-01 | APM clinics, social media and print media outlets, SITs, CAC | members | follow-up sessions based on CAHPs, BH satisfaction, peer satisfaction surveys; public listening sessions and feedback opportunities; review of complaint processes | data collected, number of sessions, new workplan elements added | Increase the number of listening sessions held by 5 sessions per year
4.2 Increase clinical best practices around equity, culturally and linguistically appropriate care, and trauma-informed environments. | 4.2.1 | 4.2.1 Offer regular provider technical assistance and education, focused on culturally and linguistically appropriate services for diverse populations; offer two equity-based trainings in the CME series per year | YCCO has partnered with George Fox to offer regular virtual CME training, including a language access training for behavioral health providers in 2021 and an anti-racism CME event in 2022. YCCO also created an distributed a Provider Language Access Toolkit for providers and is offering technical assistance around interpretation services and coding. | 2021-06-01 | 2021-06-01 | CME program, partner primary care, specialty, dental, and behavioral health clinics | providers who serve YCCO members | deliver CME sessions on specific, equity and diversity-based topics - specifically target mental health - LGBTQ community, transgender services, linguistic and culturally appropriate services | number sessions held, evaluation feedback, feedback data from members | Demonstrate increase in knowledge around cultural agility through training evaluation surveys; 6-month follow-up surveys
| 4.2.2 | 4.2.2 Collaborate with local interpretation and translation agencies to ensure quality language services and a strong workforce | Partnering with Mindlink to consider better reporting, requesting, and language service monitoring systems. Partnering with Passport to Languages to explore interpreter training and support for local workforce. | 2022-06-01 | 2022-06-01 | Mindlink, Passport to Languages, OHCIA | interpreters and translators, people requiring interpretation services | development of translation and interpretation strategy? | % of clinic encounters where need for translation was not met, % of complaints by non-English speakers, complaints from non-English speakers | Reduce rate of clinical encounters where need for translation was not met
4.3 Improve availability of medical care in rural Yamhill County. | 4.3.1 | 4.3.1 Explore feasibility of a mobile health clinic | Capitol offers regular EPDH telehealth services. Yamhill County Public Health delivered more than 20 outreach events for vaccines and testing. Virginia Garcia offered multiple testing and outreach events in their mobile clinic supported by YCCO funding. | 2021-06-01 | 2021-06-01 | Providence, VG, MDT, Public Health | members, especially rural, unengaged, and high ED users | incorporate medical services into existing mobile care delivery vans and centers | occurences of services delivered from mobile medical center | Increase rate of engagement for rural members by 3%
| 4.3.2 | 4.3.2 Expand telemedicine programs using the teledermatology and teledentristry models | Capitol offers regular EPDH telehealth services. Yamhill County Public Health delivered more than 20 outreach events for vaccines and testing. Virginia Garcia offered multiple testing and outreach events in their mobile clinic. | 2021-06-01 | 2021-06-01 | YCCO | rural members, members needing specialty care |  | rate of engagement for rurall members, track whatever telemedicine specialty addresses (like rate of skin cancer screenings or detection for telederm) | Increase rate of engagement for rural members by 12%
Priority Area
5 Trauma & Resiliency
Outcome Measure |  |  | 2018 Baseline | 2020 Update |  | Source
Increase the number of participants in nurse-family partnership by 5% |  |  | no data yet received | no data yet received | 68 clients served, 57 with an infant | YC Public Health - MMH clinic reporting
Demonstrate increase in trauma-informed care delivery through agency surveys before and after training |  |  | no training completed | training complete | training completed | Event tracker
Demonstrate increase in teacher implementation through survey results |  |  | Teacher implementation in 6 school districts | Implementation in 6 school districts; trainings in | Implementation in 5 districts, new trainings in 3 | PAX and CPW Grantee reports
Increase confidence of caretakers in parenting through outcome surveys by 5% |  |  | Children's Champion program develeoped | Program incorporated into APM contracts | Program incorporated into APM contracts | Contracts with partner clinics
Objective |  | Strategy | Narrative | Timeline |  | Partners
5
5.1 Increase protective factors that support and develop parental resilience and knowledge of child development and available resources | 5.1.1 | 5.1.1 Promote parenting classes through Mid-Valley Parenting coordination and recruitment; increase participants in parenting classes by 10% by June 2022 | 2020 - 204 parenting classes completed 2021 - 130 parenting classes completed | 2021-06-01 | 2023-06-01 | Early Learning Hub, Mid-Valley Parenting | familes with young children | Coordinate and promote quality parenting classes and workshops | # trainers, # sessions held, # participants, evaluation feedback | Outcome survey results indicate parents experience improvement in knowledge of childhood education and confidence; Increase participation in parenting classes by 10%
| 5.1.2 | 5.1.2 Collaborate with Public Health to support Nurse-Family Partnership | Nurse Family Partnership served 30 clients in 2018, 25 of of whom had an infant. In 2020 it served 68 clients, 57 with an infant. NFP continues to be part of the FamilyCore network and partners with YCCO. | 2021-06-01 | 2021-06-01 | YCPH | families with new babies and young children | Implement universal nurse-family partnership program in Yamhill County | # clients enrolled in NP Partnership | Increase the number of participants in nurse-family partnership by 5%
5.2 Increase social and emotional competence among children | 5.2.1 | 5.2.1 Fund and coordinate Good Behavior Game, Collaborative Problem Solving, and Positive Family Supports and other evidence-based prevention programs | YCCO continues to support CPW, GBG, and PFS in Willamina and McMinville School Districts, and GBG in Sheridan, Willamina, Yamhill Carlton, and Newberg. | 2020-12-01 | 2020-12-01 | YCPH, PAX GBG, PFS, Tony Biglan | school districts | Implement PAX GBG, PFS, and other evidence-based prevention program training, support, and evaluation: Develop and provide positive family engagement opportunities (family fun night at schools, positive family connections and family checkup meeting with selected parents; Develop and provide GBG family engagement opportunities (such as teaching PAX language, sharing trauma informed practices, and modeling PAX at conferences, events and back to school nights) | # staff trained, % implementation (teacher implementation survey), # schools implementing, % youth in county exposed to prevention programs, behavioral referrals, attendance, grades | Demonstrate increase in teacher implementation through survey results | outcome measures require perceived change - pre-and post- assessment
| 5.2.2 | 5.2.2 Participate in middle-school focused restorative practive workgroups with schools | Workgroups have paused. | 2021-05-01 | 2023-12-01 | YCPH, school districts | school districts, students | Participate and support coordinated middle school resource meetings, developing common practices and trauma-informed resources for middle school students and their familes | # participating school districts and community organizations, # common practices developed | Ensure 100% of school districts are represented at workgroups | Reportable and building out pre- post surveys Check program for efficacy - short term, how are we effecting change toward reducing or increasing a long-term outcome
5.3 Increase the number of trauma-informed organizations within the community | 5.3.1 | 5.3.1 Conduct 1 local multi-sector trauma-informed care assessment for at least 20 agencies | Initial survey conducted, follow up survey paused due to COVID; One training completed, 30 champions trained to implement principals in their agencies, follow up refresher workshop held | 2019-10-01 |  | YCPH, YC Family and Youth | community organizations | Survey organizations across sectors in Yamhill County, using the SAMHSA and TIO organizational self-assessment | # organizations completing assessment, # organizations adopting trauma informed trainings or policies | Demonstrate increase in trauma-informed care delivery through agency surveys before and after training
| 5.3.2 | 5.3.2 Conduct local multi-sector trauma-informed care trainings, with a focus on school systems and law enforcement by spring 2019, with at least 20 agencies represented; hold work sessions by sector every other month through December 2020 | Additional training held with more than 30 champions present; further developed workplans specific to their agencies. Trauma Informed Care Workgroup (Help the Helpers Workgroup) formed and met regularly through Q3 2021. | 2019-04-01 |  | YCPH | community organizations | Conduct trauma-informed trainings at least annually for agencies, with a focus on agencies developing trauma-informed workplans and strategies | # organizations participating in TIC training, evaluation feedback, # organizations participating in workgroup meetings | Demonstrate increase in trauma-informed care delivery through agency surveys 6 months after training
| 5.3.3 | 5.3.3 Deliver at least one cross-sector trauma training focusing on historical and generational trauma and incorporating an equity lens | 2022- Educating providers/Home Visitors - Working with Families in Addiction in August 2022, 100 participants estimated Agencies attended Trauma Informed Care Workgroup through Q3 2021 but paused to acknowledge Zoom burnout. Group is considering reconvening with support of a consultant or convening a community training. | 2021-12-01 | 2021-12-01 | Early Learning Hub | community organizations | Deliver at least one cross-sector trauma training focusing on historical and generational trauma and incorporating an equity lens | # participants, evaluation feedback | Increase knowledge of generational trauma through post-training evaluation by 20%
| 5.3.4 | 5.3.4 Promote trauma-informed care training and practices with clinics through the Children's Champion program; hold training in spring 2019; have at least five clinics participating by June 2020 | Program incorporated in key YCCO primary care partner clinics receiving value-based payments - 14 clinics | 2022-12-01 |  | Early Learning Hub, APM clinics, Family CORE Leadership Team | members with young children | Conduct trauma-informed training for YCCO clinics; encourage referral into Family CORE program | # referrals to Family CORE, participating clinics | Increase confidence of caretakers in parenting through outcome surveys by 5%
Priority Area
6 Social Determinants
Outcome Measure |  |  | 2018 Baseline | 2020 Update |  | Source
Increase number of people in community who are able to acquire vouchers by 5% per year. Increase number of people in community who are able to access affordable housing. |  |  | no data | Strategy shifted to support available affordable housing | 87 units of affordable housing made newly available in 2021. | Housing Workgroup
Increase rate of engagement with primary care for people using peer support |  |  | 61.2% engagement with physical health overall; no peer support data | 69.02% engagement physical health; no peer support data yet |  | YCCO member claims data | 2018 CHA data from claims; 2020 claims pull; physical health specifically
Double the number of people helped through SITs who are able to prevent eviction. |  |  | 35 people, $3,010 spent, 15 requests 2017-18 SIT year | $16,394 spent, 38 requests 2019-20 SIT year | 2020-21 SIT year $35,716, 77 requests met (rent assistance cap increased to $800) | SIT Workbook | SIT Workbook
Reduce the number of behavioral referrals in each school district implementing a CPW-funded program by 10%. |  |  | 70% of students respond to PAX Quiet; 60% of students take turns respectfully | No data collected; online PAX shift disrupted reporting and implentation | Behavioral referrals paused in 2021-2 school year. | PAX grantee reporting | PAX grantee reporting
Increase the number of referrals and closed-loop referrals with Family CORE and other social service programs by 25%. |  |  | Avg referrals 2018 - 60.5 per month; 726 overall | 40.5 avg; 486 total in 2019; avg 38.1 in first 5 months of 2020 | Avg. FamilyCore referrals: 26, 310 total referrals in 2020, Avg. FamilyCore referrals: 21, 254 total referrals in 2021; Avg. FamilyCore referrals: 27, 134 total referrals from Jan. to May 2022 | Family CORE referrals | Family CORE referrals
Increase the rate of engagement with primary or dental care for people who are experiencing homelessness by 5% |  |  | 61.2% physical health engagement, 8.68% dental; no reliable homelessness indicator | 69.02% physical health engagement, 7.56% dental; no reliable homelessness indicator | 71.6% engaged with primary care; no direct homeless indicator, but 19 peer service connections have been made through housing programs | YCCO member claims | YCCO member claims
Reduce the rate of hypertension in older adult members by 1% |  |  | overall hypertension - 71.7% controlled | 72.3% controlled | 67.1% controlled | YCCO member claims; incentive metric data | YCCO member claims; incentive metric data
Increase the rate of CHW engagement by 10% and retention by 5% |  |  | No data available | Engagement tracking plan developed | YCCO CHW Hub received 106 referrals, both internal and from 11 unique external agencies; 10 clients were engaged with doula services | THW Liaison reporting | THW Liaison reporting
Increase the number of people reporting barriers to services because of transportation in agency surveys by 10% |  |  | 74 NEMT complaints; 10% reported they or a family member couldn't get health care recently because of transportation | 82 NEMT complaints; 5% reported transportation is their biggest need | 3 total transportation complaints through Customer Service from 10/2020 to 10/2021 | YCCO member grievances and complaints data; 2018 CHA; 2020 housing survey | YCCO member grievances and complaints data
Objective |  | Strategy | Narrative | Timeline |  | Partners
6
6.1 Increase number of people YCCO interacts with who are connected with stable housing | 6.1.1 | 6.1.1 Partner with the housing authority to support affordable housing initiatives | YCCO awarded SHARE funding in the amount of $750,000 in 2021 for two housing projects: supported permanent housing in rural Sheridan and a short-term motel housing program in McMinnville. Funds have been approved to support the YC Housing Authority in developing an affordable housing complex in 2022. | 2019-11-01 | 2024-08-01 | YCCO, CAC |  |  |  | Increase number of people in community who are able to acquire vouchers by 5% per year.
| 6.1.2 | 6.3.4 Partner with peer support agencies to connect parents dealing with mental health challenges and/or addiction to support services, distributing materials at every peer support agency annually | Education on how and ways to seek services are shared regularly; materials share with members are in other languages other than English, and different formats YCCO partners receive information and guidance to enable referral and tracking of services, as well as troubleshooting issues that arise YCCO is assessing a list of partners, medical (physical, behavioral, dental), and social service providers | 2020-08-01 | 2020-08-01 | Service Integration Teams, United Way | community members with unstable housing | distribute funds and resource coordination for community members with unstable housing situations represented by agencies presenting cases to SITs | number of people impacted by SIT fund distribution, amount awarded, number of people facing eviction who were not evicted. | Double the number of people helped through SITs who are able to prevent eviction.
| 6.1.2 | 6.1.2 Support individual housing needs through the Service Integration Teams housing-specific fund | July 2021 to December 2022 Yamhill County Health and Human Services Department and YCCO support to prioritize housing for SIT Programs in: West Valley, Amity, Shreidan, McMinnville, Yamhill Carlton, Dayton and Newberg | 2020-06-01 | 2020-06-01 | Community Prevention and Wellness Committee | community | Grow and support Community Wellness Fund in order to foster sustainable funding for SDoH-related interventions | RFP and funding process delivered, evaluation of programs funded | Reduce the number of behavioral referrals in each school district implementing a CPW-funded program by 10%.
6.2 Develop sustainable financing strategies for continuing support of prevention and population health programs | 6.2.1 | 6.2.1 Create, grow, and steward Community Wellness Fund in order to support SDoH-related projects. | The Community Prevention and Wellness Committee created a Strategic Plan and Sustainability Plan. Budget for expansion was approved, including funding for a Development Director to grow the fund. Recruitment is ongoing. | 2021-06-01 | 2021-06-01 | ORPN, HHS, school districts, DESSA, VistaLogic | service agencies |  | implementation of referral feedback loop or data systems | Increase the number of referrals and closed-loop referrals with Family CORE and other social service programs by 25%.
| 6.2.2 | 6.2.2 Build out data systems for CPW prevention programs, feedback loop on referrals, completing evaluation of viable programs and organizational interest by June 2021 | CPW Committee is exploring grant and reporting management platform. PH-based CPW Coordinator has developed tracking systems for reporting and evaluation. Consistent funding decision rubric and reporting evaluation has been developed. | 2020-06-01 | 2020-06-01 | Community health workers, peer support agencies, drop-in centers, shelters, community meals | people experiencing homelessness | training within agencies around OHP assistance resources and OHP customer service contact, CHW referrals; CHW presence and outreach in local service agencies and shelters | materials distributed, trainings held, OHP enrollment and renewal, visits, engagement, CHW referrals | Increase the rate of engagement with primary or dental care for people who are experiencing homelessness by 5%
6.3 Increase number of people accessing social support networks and connection | 6.3.1 | 6.3.1 Reach out to homeless population through peer support centers, drop-in centers, shelters, food pantries, and other agencies by providing education and training to staff and distributing educational materials; hold one training with at least 4 agency participants by June 2020 | One listening session held at McMinnville homeless shelter; surveys distributed in Newberg Emergency overnight shelter. | 2022-06-01 | 2022-06-01 | Linfield College, senior centers, assisted living, 65+ mobile homes and apartment complexes | older adults on YCCO | partner student athletes with seniors for physical activity and social connection (biking, walking, hiking, etc) | people engaged, activity hours, health screening pre- and post | Reduce the rate of hypertension in older adult members by 1%
| 6.3.2 | 6.3.2 Physical activity intervention for older adults: partner student athletes with seniors for physical activity and social connection (biking, walking, hiking, etc), evaluating program by June 2022 | Activity has not been grant-supported as of report. | 2020-06-01 | 2020-06-01 | CHW Hub, CAC | members | distribute oral health related materials at one event in every school district catchment area per year | number of materials distributed, number of community events attended, feedback forms from events | Increase the rate of CHW engagement by 10% and retention by 5%
| 6.3.3 | 6.3.3 Increase and improve access to THWs through community outreach and education at existing events: distribute oral health related materials at one event in every school district catchment area per year | 2022 - 2 Kindergarten Registration events: Sheridan on 4/28/22 Willamina on 4/29/22 both events had vision, dental, hearing screenings along with parent survyes, the ELH sent Kinder readiness outreach materials to families in the more rural school districts YCCO provided over $49k in grants to three THW organizations (Provoking Hope, Pacific NW Doula, Yamhill Community Doula) to focus efforts to recruiting culturally diverse individuals to better respond to members' unique cultural and language needs, as well as upskilling current THWs. | 2019-12-01 | 2019-12-01 | Early Learning Hub, peer support agencies | members, specifically parents dealing with mental health challenges or addictions | promote parenting supports through peer support agencies by sharing materials, conduct trainings around parenting and family supports in peer support agencies | number of materials distributed, referral pathways established, feedback forms from events, rate of ED use for mental health issues, SPMI in ED | Increase rate of engagement with primary care for people using peer support
| 6.3.5 | 6.3.5 Work with Community Health Hub and other agencies with Traditional Health Workers to increase use of THWs and determine a tool to track outcomes | Tool identified to track outcomes: regular CHW reporting shows rate and source of referrals, allowing for outreach and engagement strategies to be adjusted according to identified need. | 2022-12-01 | 2022-12-01 | Traditional Health Worker Liaison |  |  |  | Develop system to track outcomes within traditional health work; increase member engagement with THWs by 5%
6.4 Increase the number of people with access to transportation for medical visits and other health-related needs | 6.4.1 | 6.4.1 Provide travel vouchers to at least one agency in each town in the service area Support expanded NEMT benefit and ensure care coordination for high needs members | Travel vouchers provided to two agencies and results of program were monitored and evaluated for success. Through the SITs, $4,145 of gas vouchers were disbursed from January 2021-June 2022. After voucher program was reviewd, it was deteremined that the NEMT expansion was more effective at reaching members with social needs for transit in a way that was measurable and impactful. Thus, this program was halted. | 2021-06-01 |  | Early Learning Hub | members for whom WellRide cannot meet their needs; members who need transportation to non-medical appointments | distribute travel vouchers through local service agencies, especially those in rural areas | number of vouchers distributed | Increase the number of people reporting barriers to services because of transportation in agency surveys by 10%
-
-