## CHIP 2021 Dashboard
|  |  | Key: | On track
Delayed
Paused or experiencing barriers
Strategy changed
Priority Area
1 Oral health | [5 empty] | Population | Activities | Process measurement | Outcome measurement | Notes
Outcome Measures |  |  | 2018 Baseline | 2020 Update | Source
Increase the % of children in target schools who receive dental sealants by 6% |  |  | 26.5% children 6-14 | 27.3% children 6-14 2019 | Capitol Dental claims
Demonstrate increase in consumption of fruits and vegetables through participant surveys |  |  | 0 reports received | 133 program participants reported consuming more produce | SNACK grantee report Master Gardeners' grantee report
Increase engagement with dental care for members involved with peer support by 1% |  |  | 8.86% engagement with dental care overall, no peer support data | 7.56% engagement with dental care overall, no peer support data | YCCO member claims
reduce number of cavities in members by 1% |  |  | 1.1% members with risk caries | 1.48% members with risk caries | Capitol Dental claims
Reduce the rate of cavities in students by 3% |  |  | 2.10% members <19 with risk caries | 2.01% members <19 with risk caries | Capitol Dental claims | Capitol Dental claims
Objective |  | Strategy | Narrative | Timeline | Partners | YCCO member claims
| 1 |  |  |  |  | Capitol Dental claims
1.1 Increase understanding of oral health self-care and benefits for members | 1.1.1 | 1.1.1 Coordinate and deliver school-based oral health education, for at least one grade level in each school district. | Capitol Dental provides screening and brief education in every school district in Yamhill County; program paused while schools became virtual in 2020-2021 school year | 2021-06-01 | 1-2 grade levels in each school district, Linfield, Chemeketa, and George Fox, Capitol Dental | children | oral health curriculum addition to health education classes, oral health education addition to GBG (Granny's Wacky Prizes), incorporate brushing or fluoride into school day, distribute dental supplies to schools (K-6 minimum) | supplies, consent forms, classrooms incorporating curriculum change, dental visits, dental sealants | Increase rate of dental sealants delivered to YCCO members by 6%; evaluation of oral health knowledge pre-post for GBG classrooms compared to non-GBG classrooms
| 1.1.2 | 1.1.2 Provide regular dental education, assessments, and sealants for members through existing community events, distributing educational materials at one community event in each school district area per year. | Capitol Dental provides screening and education events in Yamhill County area, including 2018 Sealants with Santa and 3 2019 Sealants with Superheros outreach events. Program paused in 2020 with outreach restrictions. | 2021-06-01 | Capitol Dental | members | distribute oral health related materials at one event in every school district catchment area per year | number of materials distributed, number of community events attended, feedback forms from events | Increase rate of dental sealants delivered to YCCO members by 6%; evaluation of oral health knowledge pre-post for school districts recieving oral health education programs/materials
1.2 Increase availability of materials, foods, and supplies that promote oral health | 1.2.1 | 1.2.1 Improve access to free dental supplies by distributing through local services agencies, especially in rural areas; establish regular dental supply deliveries in at least one service agency per town by June 2021 | Capitol Dental provides screening and education events offering oral health supplies in Yamhill County area, including 2018 Sealants with Santa and 3 2019 Sealants with Superheros outreach events. Program paused in 2020 with outreach restrictions. | 2021-06-01 | Capitol Dental | homeless members, members in unfluoridated areas | distribute free dental supplies through service agencies, schools, and partner business, targeting homeless population | Increase the % of children who receive dental sealants by 6%; reduce number of cavities in members by 2% | rate of caries among members; rate of engagement among members
| 1.2.2 | 1.2.2 Ensure access to healthy foods for key populations by funding programs like SNACK, VeggieRX, or community gardens; release RFP for funding by October 2019 | SNACK and Master Gardeners both offered programs increasing access to healthy produce; SNACK by providing Farmers' Market vouchers in McMinnville; Master Gardeners' by offering virtual cooking classes and raised bed/pot building | 2021-03-01 | food pantries, community gardens, schools, sherlters, university-based programs, churches, apartment complexes | Population - older adults and young children in rural Yamhill County area; OHP members | mobile food pantries, VeggieRx programs, SNACK, apartment or housing gardens, etc. | increase in knowledge, pre- post- survey, self-efficacy, quality of life, fruit and veggie consumpton, utilization or receipt of food, number impacted, school behavioral and attendence data, number organizations involved | Demonstrate increase in consumption of fruits and vegetables through participant surveys
1.3 Increase the number of locations members can receive dental services in the area | 1.3.1 | 1.3.1 Partner with local peer support agencies and other agencies to improve access to dental care, strengthening referral pathways and holding one training. | THW Liaison is improving training structures and resource connections with local THW agencies. | 2020-06-01 | Capitol Dental, peer support agencies | members experiencing mental health issues, substance use, or homelessness | promote oral health through peer support agencies by sharing materials, conduct trainings around oral health education in peer support agencies, colocate oral health services into peer centers | number of patients served in peer support agency settings, number of materials distributed, number of trainings conducted, training evaluation data | Increase engagement with dental care for members involved with peer support by 1%; reduce number of cavities in members by 1%
| 1.3.2 | 1.3.2 Partner with local Oral Health Coalition and Capitol Dental Care to explore teledentistry options in the community. | 22 unique locations with telecode, 7 with a claim in 2020; Capitol Dental offers a variety of teledentistry opportunities in the community; data collection processes are improving to track and document teledentristy locations | 2023-06-01 | Providence, VG, MDT, Public Health | members, especially rural, unengaged, and high ED users | incorporate teledentistry services into existing mobile and rural dental and medical clinics | occurences of services delivered using teledentistry technology | Increase the number of teledentistry tools and options available to the community | Meet and Greet – CME Spring CME – dental visit metric-related; pediatric dental visits Show MTI recruitment video Fall Meet and Greet – CME or fundraiser? Pledge program – donor levels Bring dental van for display/exhibit Keynote – Kelli Swanson-Jaecks To do: Emily reach out to CME committee – 8/28 Kyle reach out to ODA and ODHA about CE Whole group reaches out to dental contacts – tests ideas
1.4 Improve referral pathways and oral health integration efforts, including dental van volunteering | 1.4.1 | 1.4.1 Coordinate 1 oral health provider meet and greet event by December 2020 | 1 event held, 100% participants in 12.2.2020 Oral Health CME event reported learning new information to apply to practice, showed appreciation for interdiscplinary approaches | 2020-12-01 | Oral Health Coalition | providers | organize one meet-and-greet event for providers to share knowledge about integration of care, referral pathways, and develop relationships | number of events held, evaluation feedback | evaluation responses from providers before and after meet and greet (3 questions max)
1.5 Coordinate and Deliver an evidence-based oral health curriculum in YC schools to increase oral health self-care | 1.5.1 | 1.5.1 Conduct school assessment of current oral health curriculum. | Assessment of curriculum completed; determine Capitol Dental is main resource for oral health education in schools, not curriculum | 2019-10-01 | YCPH | elementary students |  |  | Assessment of curriculum compiled
| 1.5.2 | 1.5.2 Distribute oral health supplies to schools within the community. | Capitol Dental provides screening and education events offering oral health supplies in Yamhill County area, including 2018 Sealants with Santa and 3 2019 Sealants with Superheros outreach events. Program paused in 2020 with outreach restrictions. | 2021-12-01 | YCCO | elementary students |  |  | Reduce the rate of cavities in students receiving supplies by 2%
| 1.5.3 | 1.5.3 Adopt an oral health Granny's Wacky Prize for the PAX program. | PAX Coordinator left Yamhill County in 2019; PAX program changes paused in 2020 when program shifted to virtual | 2022-07-01 | YCPH and schools | elementary students |  |  | Reduce the rate of cavities in students by 3%
| 1.5.4 | 1.5.4 Incorporate oral health components to one grade health curriculum. | School-based program changes paused in 2020 when program shifted to virtual | 2020-09-01 | School districts, YCPH | elementary students |  |  | Reduce the rate of cavities in students by 1%
| 1.5.5 | 1.5.5 Adopt in-school fluoride or brushing routine in Kindergarten grade level in all rural school districts. | School-based program changes paused in 2020 when program shifted to virtual | 2021-09-01 | YCCO and Capitol and School Districts | elementary students |  |  | Reduce the rate of cavities in students in rural areas by 2%
Priority Area
2 Behavioral Health
Outcome Measures |  |  | 2018 Baseline | 2020 Update | Source
Increase rate of members attempting to quit using tobacco by 10% |  |  | 2017: 34 members of 25.5% prevalence; 32 accessing in-person classes | 52 of 22.8% prevalence; no in person classes | Yamhill County Optum Quit for Life, Willamette Valley Cancer Foundation | Yamhill County Optum Quit for Life, Willamette Valley Cancer Foundation
Demonstrate increase in knowledge for participants; increase rate of participants who advance in their field |  |  | no training offered | 4 peer support specialists with HHS advanced as Qualified Mental Health Associates. | HHS | HHS
Increase rate of people reporting suicidal ideation who do not complete suicide by 50% |  |  | 21.5/100,000 people completed suicide | 13.8/100,000 people completed suicide | 2018 Yamhill County Vital Records; 2019 HHS records | 2017, 2019 Oregon Healthy Teens YC
Reduce the number of patients receiving opioid prescriptions from multiple providers by 10% |  |  | 69.4% top prescribers in YC querying PDMP | 77.3% top presribers in YC querying PDMP | Prescribing and Drug Overdose Data Dashboard | PDMP data
Increase the rate of members accessing alternative pain management by 5% |  |  | 28 participants in Persistent Pain Program 2017 | 23 participants 2019 | YCCO member claims | YCCO member claims
Reduce the rate of patients prescribed more than 50 MED by 1% |  |  | 208 pts; 20.44/1000 people | 13.69/1,000 people | Prescribing and Drug Overdose Data Dashboard | Prescribing and Drug Overdose Data Dashboard
Reduce new rates of Hepatitis C by 1% |  |  | measure changed: 4% adults in HepC cohort screened; 423 needles given out | 9% adults screened; 926 needles collected, 426 given out | YCCO member claims; Provoking Hope Needle Exchange reporting | YCCO member claims, HepC outreach PIP; Provoking Hope and HHS Needle Exchange reporting
Objective |  | Strategy | Narrative | Timeline | Partners
2
2.1 Increase community access and awareness of tobacco cessation resources | 2.1.1 | 2.1.1 YCCO strategy: Promote Quitline through media outreach and materials in YCCO clinics by December 2019; materials available in all YCCO primary care clinics by June 2020; one informational session or training delivered for providers by December 2020 | Phone and mailer outreach through Optum; great increase in participation | 2023-12-01 | YCPH, YCCO clinics | members who use tobacco | Promote Quitline through print materials, targeted outreach, and clinic education | # Quitline users, # tobacco users | Increase rate of members attempting to quit using tobacco by 5%
| 2.1.2 | 2.1.2 YCPH Strategy: Refer organizations to smoking cessation programs and facilitator trainings | Quit for Life outreach meetings held in 2 clinics and with provider-inclusive stakeholder meetings; YCPH resource shifts due to COVID resulted in delay | 2021-06-01 | YCPH- Cessation Materials ALA- Cessation programs and facilitator trainings American Cancer Society- Cessation Programs | YCCO clinics, peer support centers, shelters and food pantries, social service agencies | Deliver and share education materials around smoking cessation programs and facilitator trainings | # Quitline users, # tobacco users | Increase rate of members attempting to quit using tobacco by 1%
| 2.1.3 | 2.1.3 YCPH Strategy: Infuse tobacco cessation referral and counseling into Home Visiting programs and training | Tobacco Prevention, Education, and Promotion Coordinator shifted scope to COVID response; strategy delayed. | 2020-12-01 | YCPH, Home visitor network, YCCO Family CORE Leadership | members who use tobacco | Deliver one training for home visiting network sharing information about motivation interviewing for tobacco cessation, Quitline referral pathways, and quit resources | # Quitline users, # participants | Increase rate of members who are parents attempting to quit using tobacco by 10%
2.2 Increase community-wide evidence-based suicide prevention trainings | 2.2.1 | 2.2.1 Offer upskilling and additional training for 15 existing peer support specialists, volunteers, and mental health employees by December 2022 | THW Liaison hired, technical support and assistance offered, systems implemented: analysis of current system, strategies developed to enhance policies, develop payment structures, SDoH investments, coordination of services, and capacity building | 2021-12-01 | YCCO, peer support agencies, HHS | volunteers and employees in mental-health related fields | Coordinate and promote training for mental health service providers to encourage local mental health providers are hired, professionally developed, and retained in the community | # participants in training, trainings held, scholarships offered, evaluation feedback | Demonstrate increase in knowledge for participants; increase rate of participants who advance in their field
| 2.2.2 | 2.2.2 Improve promotion of services via print materials, social media, and other awareness activities | Trainings held with fewer than 10 organizations due to COVID delays; engagement increasing in 2022; YCCO member engagement workgroup begun with strategies around member outreach | 2021-06-01 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members, general community | sharing information through the following methods: print materials through posting and mail, website and social media, in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, agencies involved | Increase rate of people reporting suicidal ideation who do not complete suicide by 50%
2.3 Increase awareness, education and utilization of pain management alternatives and appropriate prescription pain management | 2.3.1 | 2.3.1 Promote Prescription Drug Monitoring Program use among non-primary care providers | Yamhill County Opioid workgroup continues convening and discussing PDMP engagement | 2020-11-01 | YCPH | specialty and oral health care providers |  |  | Reduce the number of patients receiving opioid prescriptions from multiple providers by 10%
| 2.3.2 | 2.3.2 Review non-opioid pain management benefit options and services for YCCO members | 2020 summit featured alternative pain treament methodologies- increasing focus on PT and chiro, etc. | 2023-11-01 | YCCO | members experiencing chronic pain | assess covered alternative medicine benefits; promote available services and ensure providers have access to accurate information regarding alternative care benefits and referral and prior authorization activities | member feedback and complaints regarding alternative care; | rate of engagement with alternative pain management covered by YCCO; Compile alternative pain management resource guide; increase the rate of members accessing alternative pain management by 5%
| 2.3.3 | 2.3.3 Promote Oregon Pain Guidance practices to providers and community partners | Opioid-focused CME event held February 2021; Provider E-News offers regular updates | 2020-12-01 | YCPH | providers and community partners | disseminate Pain Guidance information through provider network, serve as technical assistance resource for community regarding pain guidelines | # providers and agencies reached | Reduce the rate of patients prescribed more than 50 MED by 1%
| 2.3.4 | 2.3.4 Host one annual Opioid Summit to update the provider, community partners and community members about best practices and available resources | Opioid-focused CME event held February 2021 | 2019-11-01 | YCPH | providers and community partners | Hold annual training for providers who work with patients experiencing pain, establish common understanding of current issues and best practices to address them | # participants, evaluation feedback | Reduce the rate of patients prescribed more than 50 MED; Demonstrate relevant information learned during Summit
| 2.3.5 | 2.3.5 Support community needle exchange program; launching program by December 2019; incorporating medical staff by 2022 | Program is now operating at 4 different locations and the van is available somewhere Monday - Thursday with sweeps Fridays. | 2020-12-01 | YCPH, peer support | members who use drugs intravenously | Support needle exchange program, both mobile and fixed site delivery with additional peer or educational supports built in; incorporate medical staff by 2022 | # participants, rate of intravenous drug use-related disease, # materials distributed to participants, # needles provided and collected | Hepatitis C rates among members by 1%, % of wound-related ED visits
Priority Area
3 Children and Families
Outcome Measure |  |  | 2018 Baseline | 2020 Update | Source
Increase the rate of families connected to home visiting and other services |  |  | Avg Family CORE referrals: 60.5 per month; 726 overall | Avg Family CORE referrals: 40.5, 486 total in 2019; avg 38.1 in first 5 months of 2020 | Family CORE referrals | YCCO claims data, incentive metric reports; Family CORE referrals
Decrease rate of postpartum depression by 2% |  |  | 11 diagnoses, ~3.6% of births | 33 diagnoses, ~11% of births | YCCO member claims | YCCO member claims
Increase rate of dental screenings held in nonclinical settings by 10%; reduce rate of cavities in student by 2% |  |  | no data available for nonclinical settings | 2% of visits in nonclinical settings | Capitol Dental claims | Capitol Dental claims
Increase the rate of children receiving well-visits by 6% |  |  | 66.2% well-child | 62.2 well child 3-6 | YCCO member claims, incentive metric reports
increase Kindergarten Assessment Scores |  |  | Approaches to Learning total: 3.6 avg rating/5 Early Math: 11.2 avg correct/16 Uppercase letter recognition: 14.4 avg correct/26 | Approaches to Learning total: 3.6 avg rating/5 Early Math: 11 avg correct/16 Uppercase letter recognition: 14.1 avg correct/26 | Oregon Department of Education KA Scores
Objective |  | Strategy | Narrative | Timeline | Partners
3
3.1 Increase evidence-based care models that support community members, health care providers, and social service providers in achieving planned pregnancies | 3.1.1 | 3.1.1 Work with peer support agencies and other social service agencies to increase referrals to programs like Family CORE and encourage home visiting | THW Liaison and Outreach and Referral Coordinator working to coordinate with Family CORE within network | 2021-06-01 |  |  |  |  | Increase the rate of children receiving well-visits by 6%; Increase the rate of post-partum well-visits by 6%
| 3.1.2 | 3.1.2 Conduct Family Wellbeing Assessment in all MMHs for all patients by June 2020. Connect at-risk mothers to behaviorist and home visiting supports. | Contracts established to collect this screening data. No data yet available. | 2020-06-01 | HHS/Public Health, YCCO | families with new babies | deliver and evaluate Family Well-Being Assessment for trauma scores and connect families with services if needed | number of assessments delivered, number of referrals made | Increase the number of screenings delivered by 25%
3.2 Create and implement a reproductive health education and marketing campaign. | 3.2.1 | 3.2.1 Distribute health promotion materials and information through a wide range of media, promoting availability of benefits, prenatal and postpartum care, CHW and doula supports, and family supports, and other health information and education by December 2021 | Member Engagement Workgroup formed to advise and strategize effective member outreach activities and evaluate for effectiveness | 2021-12-01 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members of childbearing age | sharing information through the following methods: print materials through posting and mail, website and social media, in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, number of clinic calls and appointments made, effective contraceptive use; rate of engagement with prenatal care, rate of postpartum visits, % ECU, health births?, engagement with doula supports, rate of members accessing home visiting services | Increase the rate of children receiving well-visits by 6%; Increase the rate of post-partum well-visits by 6%; decrease rate of post-partum depression by 2%
3.3 Increase the availability of health-related services and screening at family-oriented events and activities | 3.3.1 | 3.3.1 Provide dental/vision/hearing screenings at annual Family Play Day outreach event and at Kinder Registration in three school districts by December 2021 | 2019 event had vision, dental, hearing screening; no event in 2020 | 2021-06-01 | Early Learning Hub | families with children | offer medical screenings at Kinder Registration events in at least 3 school districts and at annual Family Play Day Event | number of materials distributed, number of community events attended, feedback forms from events | Increase rate of dental screenings held in non-clinical settings by 10%; reduce rate of cavities in student by 2%
| 3.3.2 | 3.3.2 Partner with 4 rural libraries to conduct outreach to families of children 0-5 and connect them to school readiness, family support, and healthcare services by June 2021 | Early Learning attended 34 events in 2019, including 6 at libraries, reaching over 840 people; during 2020, the ELH sent Kinder readiness outreach materials to families in the more rural school districts | 2021-06-01 | Early Learning Hub | rural families with young children | attend rural library events and share materials with rural libraries around family support services | number of materials shared, number of events attended, number of referrals made from libraries | Increase the rate of children receiving well-visits by 6%; increase Kindergarten Assessment scores; increase rate of children from Spanish-speaking families receiving well-visits by 6%
| 3.3.3 | 3.3.3 Ensure access to healthy foods and physical activity for families by by funding programs like SNACK, VeggieRX, or community gardens. | SNACK and Master Gardeners both offered programs increasing access to healthy produce; SNACK by providing Farmers' Market vouchers in McMinnville; Master Gardeners' by offering virtual cooking classes and raised bed/pot building | 2021-03-01 | CAC | Families and children | Release an RFP and fund programs that are related to nutrition and physical activity |  | Demonstrate increase in consumption of fruits and vegetables through participant surveys ; increase the number of families connected to health-related services by 10%
Priority Area
4 Access to Care
Outcome Measure |  |  | 2018 Baseline | 2020 Update | Source
Increase engagement with primary care for people living in rural areas by 9% |  |  | 88.5% | 83.6% | YCCO claims data, incentive metric reports; Family CORE referrals | YCCO member claims
Increase rate of engagement for rural members by 12% |  |  | 88.5% | 83.6% | Capitol Dental claims | YCCO member claims
Demonstrate increase in knowledge around cultural agility through training evaluation surveys; 6-month follow-up surveys |  |  | 0 equity-based trainings offered | 1 trauma CME offered, one scheduled | SNACK grantee report, OSU grantee report | CME post-event surveys
Reduce rate of clinical encounters where need for translation was not met |  |  | no data available | 75% members receiving language services don't have translation indicator in file | Claims, Mindlink and Passport to Languages invoices, clinic survey data | data process developing
Objective |  | Strategy | Narrative | Timeline | Partners
4
4.1 Increase community awareness of available services, rights, and benefits | 4.1.1 | 4.1.1 Distribute health promotion materials and information through a wide range of media, sharing healthy living information and education, benefit and resource information, member rights and advocacy, and invitations to engage | Member Engagement Workgroup formed to advise and strategize effective member outreach activities and evaluate for effectiveness; Early Learning attended 34 events in 2019, including 6 at libraries, reaching over 840 people; during 2020, the ELH sent Kinder readiness outreach materials to families in the more rural school districts | 2022-06-01 | print media outlets, social media outlets, service agencies and community partners serving OHP membes, CAC | members, especially those unengaged with care or high ED utilizers | sharing information through the following methods: print materials through posting and mail, website and social media, targeted member phone calls (stratify by high risk tier members who are unengaged after 6 months of enrollment), in-person engagement at events and through CHW meetings, promotion through community partner training | materials distributed, number of clinic calls and appointments made, ED utilization, contacts to customer service, screening rates, number of members actually contacted | Increase engagement with primary care for people living in rural areas by 9%; increase rate of people who are successfully engaged by phone or in-person within the first six months of enrollment to 70% | YCCO will provide community education on benefits to new and high risk OHP within the first 6 months of enrolling into the program though a multi media system; Build relationship with social services agency to provide wraparound services to OHP by provide educational materials on program eligibility for additional services. New member call from community workers on welcoming to OHP, streamline communication and building relationships with members. Navigator to help member utilize the system when they first join OHP.
| 4.1.2 | 4.1.2 Hold regular listening sessions and conduct regular surveys, in collaboration with clinics, to obtain feedback from patients, clients, and community members; Hold one listening session in each school district catchment area every two years; deliver surveys in at least one clinic annually | Housing survey conducted; YCCO Community Conversation held in 2021 - 48 attendees; in-person outreach to increase in 2021 | 2022-06-01 | APM clinics, social media and print media outlets, SITs, CAC | members | follow-up sessions based on CAHPs, BH satisfaction, peer satisfaction surveys; public listening sessions and feedback opportunities; review of complaint processes | data collected, number of sessions, new workplan elements added | Increase the number of listening sessions held by 5 sessions per year
4.2 Increase clinical best practices around equity, culturally and linguistically appropriate care, and trauma-informed environments. | 4.2.1 | 4.2.1 Offer regular provider technical assistance and education, focused on culturally and linguistically appropriate services for diverse populations; offer two equity-based trainings in the CME series per year | CME series offered in 2021; 4 events per year focused on integrated education models for all kinds of providers | 2021-06-01 | CME program, partner primary care, specialty, dental, and behavioral health clinics | providers who serve YCCO members | deliver CME sessions on specific, equity and diversity-based topics - specifically target mental health - LGBTQ community, transgender services, linguistic and culturally appropriate services | number sessions held, evaluation feedback, feedback data from members | Demonstrate increase in knowledge around cultural agility through training evaluation surveys; 6-month follow-up surveys
| 4.2.2 | 4.2.2 Collaborate with local interpretation and translation agencies to ensure quality language services and a strong workforce | Collaboration with language services partners; technical assistance from Oregon Health Authority and Office of Equity and Inclusion; data processes for assessing and evaluating language services in place | 2022-06-01 | Mindlink, Passport to Languages, OHCIA | interpreters and translators, people requiring interpretation services | development of translation and interpretation strategy? | % of clinic encounters where need for translation was not met, % of complaints by non-English speakers, complaints from non-English speakers | Reduce rate of clinical encounters where need for translation was not met
4.3 Improve availability of medical care in rural Yamhill County. | 4.3.1 | 4.3.1 Explore feasibility of a mobile health clinic | Needle exchange offers mobile health; COVID created need for multiple mobile outreach models that YCCO has supported financially and through resources | 2021-06-01 | Providence, VG, MDT, Public Health | members, especially rural, unengaged, and high ED users | incorporate medical services into existing mobile care delivery vans and centers | occurences of services delivered from mobile medical center | Increase rate of engagement for rural members by 3%
| 4.3.2 | 4.3.2 Expand telemedicine programs using the teledermatology and teledentristry models | Capitol Dental provides screening and education events in Yamhill County area, including 2018 Sealants with Santa and 3 2019 Sealants with Superheros outreach events. Program paused in 2020 with outreach restrictions. COVID created need for multiple mobile outreach models that YCCO has supported financially and through resources | 2021-06-01 | YCCO | rural members, members needing specialty care |  | rate of engagement for rurall members, track whatever telemedicine specialty addresses (like rate of skin cancer screenings or detection for telederm) | Increase rate of engagement for rural members by 12%
Priority Area
5 Trauma & Resiliency
Outcome Measure |  |  | 2018 Baseline | 2020 Update | Source
Increase the number of participants in nurse-family partnership by 5% |  |  | no data yet received | no data yet received | YC Public Health - MMH clinic reporting
Demonstrate increase in trauma-informed care delivery through agency surveys before and after training |  |  | no training completed | training complete | Event tracker
Demonstrate increase in teacher implementation through survey results |  |  | Teacher implementation in 6 school districts | Implementation in 6 school districts; trainings in | PAX and CPW Grantee reports
Increase confidence of caretakers in parenting through outcome surveys by 5% |  |  | Children's Champion program develeoped | Program incorporated into APM contracts | Contracts with partner clinics
Objective |  | Strategy | Narrative | Timeline | Partners
5
5.1 Increase protective factors that support and develop parental resilience and knowledge of child development and available resources | 5.1.1 | 5.1.1 Promote parenting classes through Mid-Valley Parenting coordination and recruitment; increase participants in parenting classes by 10% by June 2022 | Some increases in engagement in the virtual space; some parents prefer the flexibility of online classes and report benefits from the connection. 9 classes delivered in 2018-19. | 2021-06-01 | Early Learning Hub, Mid-Valley Parenting | familes with young children | Coordinate and promote quality parenting classes and workshops | # trainers, # sessions held, # participants, evaluation feedback | Outcome survey results indicate parents experience improvement in knowledge of childhood education and confidence; Increase participation in parenting classes by 10%
| 5.1.2 | 5.1.2 Collaborate with Public Health to support Nurse-Family Partnership | Family Well-Being Council formed to advise home visiting process and family priorities | 2021-06-01 | YCPH | families with new babies and young children | Implement universal nurse-family partnership program in Yamhill County | # clients enrolled in NP Partnership | Increase the number of participants in nurse-family partnership by 5%
5.2 Increase social and emotional competence among children | 5.2.1 | 5.2.1 Fund and coordinate Good Behavior Game, Collaborative Problem Solving, and Positive Family Supports and other evidence-based prevention programs | Good Behavior Game program shifted to virtual model in 2020; trainings continued virtually for local school districts, including PAX Partner trainings | 2020-12-01 | YCPH, PAX GBG, PFS, Tony Biglan | school districts | Implement PAX GBG, PFS, and other evidence-based prevention program training, support, and evaluation: Develop and provide positive family engagement opportunities (family fun night at schools, positive family connections and family checkup meeting with selected parents; Develop and provide GBG family engagement opportunities (such as teaching PAX language, sharing trauma informed practices, and modeling PAX at conferences, events and back to school nights) | # staff trained, % implementation (teacher implementation survey), # schools implementing, % youth in county exposed to prevention programs, behavioral referrals, attendance, grades | Demonstrate increase in teacher implementation through survey results | outcome measures require perceived change - pre-and post- assessment
| 5.2.2 | 5.2.2 Participate in middle-school focused restorative practive workgroups with schools | Restorative practice workgroup formed, but delayed due to competing priorities | 2021-05-01 | YCPH, school districts | school districts, students | Participate and support coordinated middle school resource meetings, developing common practices and trauma-informed resources for middle school students and their familes | # participating school districts and community organizations, # common practices developed | Ensure 100% of school districts are represented at workgroups | Reportable and building out pre- post surveys Check program for efficacy - short term, how are we effecting change toward reducing or increasing a long-term outcome
5.3 Increase the number of trauma-informed organizations within the community | 5.3.1 | 5.3.1 Conduct 1 local multi-sector trauma-informed care assessment for at least 20 agencies | Initial survey conducted, follow up survey paused due to COVID; One training completed, 30 champions trained to implement principals in their agencies, follow up refresher workshop held | 2019-10-01 | YCPH, YC Family and Youth | community organizations | Survey organizations across sectors in Yamhill County, using the SAMHSA and TIO organizational self-assessment | # organizations completing assessment, # organizations adopting trauma informed trainings or policies | Demonstrate increase in trauma-informed care delivery through agency surveys before and after training
| 5.3.2 | 5.3.2 Conduct local multi-sector trauma-informed care trainings, with a focus on school systems and law enforcement by spring 2019, with at least 20 agencies represented; hold work sessions by sector every other month through December 2020 | One training completed, 30 champions trained to implement principals in their agencies, follow up refresher workshop held | 2019-04-01 | YCPH | community organizations | Conduct trauma-informed trainings at least annually for agencies, with a focus on agencies developing trauma-informed workplans and strategies | # organizations participating in TIC training, evaluation feedback, # organizations participating in workgroup meetings | Demonstrate increase in trauma-informed care delivery through agency surveys 6 months after training
| 5.3.3 | 5.3.3 Deliver at least one cross-sector trauma training focusing on historical and generational trauma and incorporating an equity lens | No training held yet; CME on trauma-informed dental care schedule for June | 2021-12-01 | Early Learning Hub | community organizations | Deliver at least one cross-sector trauma training focusing on historical and generational trauma and incorporating an equity lens | # participants, evaluation feedback | Increase knowledge of generational trauma through post-training evaluation by 20%
| 5.3.4 | 5.3.4 Promote trauma-informed care training and practices with clinics through the Children's Champion program; hold training in spring 2019; have at least five clinics participating by June 2020 | Program incorporated in key YCCO primary care partner clinics receiving value-based payments - 14 clinics | 2022-12-01 | Early Learning Hub, APM clinics, Family CORE Leadership Team | members with young children | Conduct trauma-informed training for YCCO clinics; encourage referral into Family CORE program | # referrals to Family CORE, participating clinics | Increase confidence of caretakers in parenting through outcome surveys by 5%
Priority Area
6 Social Determinants
Outcome Measure |  |  | 2018 Baseline | 2020 Update | Source
Increase number of people in community who are able to acquire vouchers by 5% per year. |  |  | no data | Strategy shifted to support available affordable housing | Housing Workgroup
Increase rate of engagement with primary care for people using peer support |  |  | 61.2% engagement with physical health overall; no peer support data | 69.02% engagement physical health; no peer support data yet | YCCO member claims data | 2018 CHA data from claims; 2020 claims pull; physical health specifically
Double the number of people helped through SITs who are able to prevent eviction. |  |  | 35 people, $3,010 spent, 15 requests 2017-18 SIT year | $16,394 spent, 38 requests 2019-20 SIT year | SIT Workbook | SIT Workbook
Reduce the number of behavioral referrals in each school district implementing a CPW-funded program by 10%. |  |  | 70% of students respond to PAX Quiet; 60% of students take turns respectfully | No data collected; online PAX shift disrupted reporting and implentation | PAX grantee reporting | PAX grantee reporting
Increase the number of referrals and closed-loop referrals with Family CORE and other social service programs by 25%. |  |  | Avg referrals 2018 - 60.5 per month; 726 overall | 40.5 avg; 486 total in 2019; avg 38.1 in first 5 months of 2020 | Family CORE referrals | Family CORE referrals
Increase the rate of engagement with primary or dental care for people who are experiencing homelessness by 5% |  |  | 61.2% physical health engagement, 8.68% dental; no reliable homelessness indicator | 69.02% physical health engagement, 7.56% dental; no reliable homelessness indicator | YCCO member claims | YCCO member claims
Reduce the rate of hypertension in older adult members by 1% |  |  | overall hypertension - 71.7% controlled | 72.3% controlled | YCCO member claims; incentive metric data | YCCO member claims; incentive metric data
Increase the rate of CHW engagement by 10% and retention by 5% |  |  | No data available | Engagement tracking plan developed | THW Liaison reporting | THW Liaison reporting
Increase the number of people reporting barriers to services because of transportation in agency surveys by 10% |  |  | 74 NEMT complaints; 10% reported they or a family member couldn't get health care recently because of transportation | 82 NEMT complaints; 5% reported transportation is their biggest need | YCCO member grievances and complaints data; 2018 CHA; 2020 housing survey | YCCO member grievances and complaints data
Objective |  | Strategy | Narrative | Timeline | Partners
6
6.1 Increase number of people YCCO interacts with who are connected with stable housing | 6.1.1 | 6.1.1 Partner with the housing authority to increase transparency of housing voucher process | Strategy shifted; partnered with Housing Authority to develop housing complex survey to understand need; support housing initiatives through SHARE | 2019-11-01 | YCCO, CAC |  |  |  | Increase number of people in community who are able to acquire vouchers by 5% per year.
| 6.1.2 | 6.3.4 Partner with peer support agencies to connect parents dealing with mental health challenges and/or addiction to support services, distributing materials at every peer support agency annually | Education on how and ways to seek services are shared regularly; materials share with members are in other languages other than English, and different formats YCCO partners receive information and guidance to enable referral and tracking of services, as well as troubleshooting issues that arise YCCO is assessing a list of partners, medical (physical, behavioral, dental), and social service providers | 2020-08-01 | Service Integration Teams, United Way | community members with unstable housing | distribute funds and resource coordination for community members with unstable housing situations represented by agencies presenting cases to SITs | number of people impacted by SIT fund distribution, amount awarded, number of people facing eviction who were not evicted. | Double the number of people helped through SITs who are able to prevent eviction.
| 6.1.2 | 6.1.2 Support individual housing needs through the Service Integration Teams housing-specific fund | United Way grant and additional YCCO support to prioritize housing | 2020-06-01 | Community Prevention and Wellness Committee | community | Grow and support Community Wellness Fund in order to foster sustainable funding for SDoH-related interventions | RFP and funding process delivered, evaluation of programs funded | Reduce the number of behavioral referrals in each school district implementing a CPW-funded program by 10%.
6.2 Develop sustainable financing strategies for continuing support of prevention and population health programs | 6.2.1 | 6.2.1 Create, grow, and steward Community Wellness Fund in order to support SDoH-related projects. | Focus shifted to retraining teachers in virtual space; partnership with Georgia Health Policy Institute continues; alignment with HRS | 2021-06-01 | ORPN, HHS, school districts, DESSA, VistaLogic | service agencies |  | implementation of referral feedback loop or data systems | Increase the number of referrals and closed-loop referrals with Family CORE and other social service programs by 25%.
| 6.2.2 | 6.2.2 Build out data systems for CPW prevention programs, feedback loop on referrals, completing evaluation of viable programs and organizational interest by June 2021 | Delays due to staff turnover and shift to virtual implementation; CIE development in place to support additional feedback loop priorities | 2020-06-01 | Community health workers, peer support agencies, drop-in centers, shelters, community meals | people experiencing homelessness | training within agencies around OHP assistance resources and OHP customer service contact, CHW referrals; CHW presence and outreach in local service agencies and shelters | materials distributed, trainings held, OHP enrollment and renewal, visits, engagement, CHW referrals | Increase the rate of engagement with primary or dental care for people who are experiencing homelessness by 5%
6.3 Increase number of people accessing social support networks and connection | 6.3.1 | 6.3.1 Reach out to homeless population through peer support centers, drop-in centers, shelters, food pantries, and other agencies by providing education and training to staff and distributing educational materials; hold one training with at least 4 agency participants by June 2020 | Community Health Worker Hub performs regular outreach activites; staff turnover and COVID paused outreach safety and ability; no definitive homelessness data (no address, denominator is too small to draw conclusions with actual homeless indicator) | 2022-06-01 | Linfield College, senior centers, assisted living, 65+ mobile homes and apartment complexes | older adults on YCCO | partner student athletes with seniors for physical activity and social connection (biking, walking, hiking, etc) | people engaged, activity hours, health screening pre- and post | Reduce the rate of hypertension in older adult members by 1%
| 6.3.2 | 6.3.2 Physical activity intervention for older adults: partner student athletes with seniors for physical activity and social connection (biking, walking, hiking, etc), evaluating program by June 2022 | Included in 2018 request for CHIP grant proposals, no applicants; project paused until next grant cycle | 2020-06-01 | CHW Hub, CAC | members | distribute oral health related materials at one event in every school district catchment area per year | number of materials distributed, number of community events attended, feedback forms from events | Increase the rate of CHW engagement by 10% and retention by 5%
| 6.3.3 | 6.3.3 Increase and improve access to THWs through community outreach and education at existing events: distribute oral health related materials at one event in every school district catchment area per year | THW services do not require PAs There is a strong emphasis and support to diversify the workforce and YCCO aims to provide the tools and create an environment to enable cultural and ethnic diversification, inclusion, utilization, and advancement of traditional health workers. | 2019-12-01 | Early Learning Hub, peer support agencies | members, specifically parents dealing with mental health challenges or addictions | promote parenting supports through peer support agencies by sharing materials, conduct trainings around parenting and family supports in peer support agencies | number of materials distributed, referral pathways established, feedback forms from events, rate of ED use for mental health issues, SPMI in ED | Increase rate of engagement with primary care for people using peer support
| 6.3.5 | 6.3.5 Work with Community Health Hub and other agencies with Traditional Health Workers to increase use of THWs and determine a tool to track outcomes | Tools to capture utilization will be improved upon in the later years with hopes to reduce the burden on reporting. YCCO uses several blended payment methods to support THW program delivery and does not rely on fee-for-service only. There is ongoing work to ascertain payment models best for individual organizations in respect to the types of services rendered. | 2022-12-01 | Traditional Health Worker Liaison |  |  |  | Develop system to track outcomes within traditional health work; increase member engagement with THWs by 5%
6.4 Increase the number of people with access to transportation for medical visits and other health-related needs | 6.4.1 | 6.4.1 Provide travel vouchers to at least one agency in each town in the service area | $5,600 worth travel vouchers disbursed in the community through 4 agencies | 2021-06-01 | Early Learning Hub | members for whom WellRide cannot meet their needs; members who need transportation to non-medical appointments | distribute travel vouchers through local service agencies, especially those in rural areas | number of vouchers distributed | Increase the number of people reporting barriers to services because of transportation in agency surveys by 10%
-
-